## Main
Scrum Project
| Product | Elderly Health Monitoring and Alert System
| Active versions | 2.0
|  |  |  | Product Owner | Jan Samuelsson
| Team |  |  | Other Stakeholders
| Scrum Master | Thang, Huynh Minh
| Developers | Dung, Mai Van
Khoa, Nguyen Khac Nguyen
Cuong, Truong Manh
Duy, Vo Le
| Projects | [5 empty] | Sprint Plan
| Id | Initial | Start | End | Status | Remarks | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
| 1 | Initial | Aug 15th, 2025 | Aug 20th, 2025 | Done |  | 1 | Aug 21th, 2025 | Aug 31st, 2025 | Completed
| 2 | Sprint 1 | Aug 21th, 2025 | Aug 31st, 2025 | Done |  | 2 | Sep 1st, 2025 | Oct 5th, 2025 | Completed
| 3 | Sprint 2 | Sep 1st, 2025 | Oct 5th, 2025 | Done |  | 3 | Oct 6th, 2025 | Nov 15th, 2025 | Completed
| 4 | Sprint 3 | Oct 6th, 2025 | Nov 15th, 2025 | Done |  | 4 | Nov 16th, 2025 | Dec 10th, 2025 | Completed
| 5 | Sprint 4 | Nov 16th, 2025 | Dec 10th, 2025 | Done
| 6 | Project meeting | Dec 17th, 2025 | Dec 18th, 2025 | Done
| 7 | Final realease | Dec 20th, 2025 | Dec 20th,2025

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Priority | Sprint No | Estimate (Hours)
PB01 | Register | Personal User | Create an account | I can login with my own account to access the website | - Username must not contain spaces and not be accented - Password must be > 8 characters, < 16 characters include uppercase letters, lowercase letters, numbers and special characters. | 5 | 1 | 40
PB02 | Login | Personal User | Login to website | To access my HomePage | - Login with facebook and gmail - Input data to enter: + Username accepted + Password accepted | 5 | 1 | 35
PB03 | Log out | Personal User | Log out from the currently account | I can exit my account whenever I want | - Click the "log out" button - Exit from the currently account | 5 | 1 | 30
PB04 | Forgot password | Personal User | Recover password when forgot | I can change my password into the new one and get my account back | - Click "Forgot password" button - Use the link sent to the account's email which registered in profile to change the new password | 5 | 2 | 35
PB05 | Send verify account request | Personal User | Verify the account | My account can look more reputable | - Click "Send verify" button - Send verification code to gmail account - Enter the verification code that matches the code sent to gmail | 5 | 2 | 35
PB06 | HomePage | Personal User | Access the HomePage | I can see an overview of available features and quickly navigate to what I need. | - Successfully accessed HomePage - Display main functions - Navigate to another page | 4 | 2 | 25
PB07 | Monitoring | Personal User | Access the Monitoring page | I can view real-time status or activity data relevant to my account or devices. | - Go to Monitoring page - Show activity data - Details of each activity (if any) | 4 | 2 | 30
PB08 | Weight and BMI | Personal User | Access to Visit the weight and BMI page | I can look at my BMI and use that to change my diet or water intake. | - Enter or update height, weight - View BMI classification - Show my BMI | 5 | 3 | 30
PB09 | Doctor AI | Personal User | Access to Visit the doctor AI | I can ask the doctor simple questions about my symptoms, whether they are serious and whether I should see a doctor. | - Visit Ask a Doctor - Submit a symptom question - Get a severity rating | 3 | 4 | 25
PB10 | Setting | Personal User | I want to access the settings | I can change some personal information or language used | - Go to personal settings page - Edit personal information - Change system language | 4 | 3 | 35
PB11 | Blood pressure | Personal User | I want to access the blood pressure page | I can check if my blood pressure changes during the day. | - View current application - Log changes during the day - Enter pressure index (if not using device) | 3 | 4 | 30
PB12 | Blood sugar | Personal User | I want to access the settings | I can check to see if my blood sugar fluctuates during the day. | - View current blood sugar level - Manually enter blood sugar level - Track blood sugar fluctuations during the day | 3 | 4 | 30
PB13 | Water Remind | Personal User | Ceceive regular reminders to drink water during the day | I can maintain good hydration and improve my health | - User can set daily water intake goal (e.g., 2000 ml/day) - App automatically sends notifications every X hours - User can log each time they drink water - The dashboard updates hydration progress in percentage - Option to enable/disable or customize reminder frequency | 5 | 3 | 40
PB14 | Fall report log | Personal User | Review historical fall incidents | I can analyze my risk patterns | - View fall history list - Filter by date | 5 | 3 | 40
PB15 | Alert | Personal User | I want to receive alerts from the app | I can check if my user has a life-threatening fall. | - Detect dangerous falls - Send warnings to users (Change Alert button color) - Record fall history | 5 | 2 | 40
PB16 | Medical Contact | Personal User | Make an emergency call directly from the app | I can quickly reach medical support | - Afer receiving alert, user press button "Liên hệ y ế" - System will make a call to the nearest hospital | 4 | 3 | 40
PB17 | Login | Admin | Login to website | I can login with my account as an administrator | - Login with gmail - Input data to enter: + Username accepted + Password accepted | 5 | 1 | 30
PB18 | Forgot password | Admin | Recover password when forgot | I can change my password into the new one and get my account back | - Click "Forgot password" button - Use the link sent to the account's email which registered in profile to change the new password | 5 | 2 | 30
PB19 | Send verify account request | Admin | Verify the account | My account can look more reputable | - Click "Send verify" button - Send photos of ID Card in both side - Send picture of user's face | 5 | 2 | 30
PB20 | DashBoard | Admin | View a dashboard | I can see an overview of key system metrics and recent activity at a glance. | - View dashboard overview - View recent activity - View the new users | 5 | 2 | 40
PB21 | Manage Accounts | Admin | Manage user accounts | I can approve, edit, deactivate, or remove users when necessary | - View user list - Edit user - Search or filter users | 5 | 3 | 30
PB22 | Device management | Admin | Manage connected devices | I can monitor their status, approve new devices, or disable malfunctioning ones | - View device list - Approve pending device - Disable or remove device | 5 | 2 | 40
PB23 | Registration approval | Admin | Review and approve or reject new user registrations | I can check only valid users gain access to the system | - View pending registrations - Approve or reject registration - View applicant details | 5 | 3 | 45
PB24 | History of activities | Admin | View the history of user or system activities | I can audit actions and track usage | - View activity log - View action details | 1 | 4 | 20
PB25 | Backend Arch | System | Setup Backend Architecture | The system has a stable API and DB connection. | - Node.js environment ready - API Gateway configured - DB connection successful | 4 | 1 | 45
PB26 | Basic Database | System | Establish Basic Database | User data stored in DB | - PostgreSQL installed - Users/Roles tables created | 4 | 1 | 40
PB27 | Fall Alert Logic | System | Detect Fall Logic | System detects falls from sensors | - Detect fall event from video/sensor - Generate timestamp - Trigger alert signal | 5 | 2 | 60
PB29 | Video Handler | System | Handle Video/Image | Media processed from AI | - Receive video stream - Save file to storage server | 5 | 3 | 70
PB30 | Cam Connect | System | Connect Camera | Real-time video streaming | - IP Camera connected - Stream viewable on backend | 5 | 3 | 80

## Sprint 1 Backlog
Sprint Backlog 1
Sprint Id | Backlog Id | Description | Owner | Status | Estimate | Completed | Pending | Total effort | Effort vs Estimate | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day 10
1.1 | PB01 | Design UI | Khoa | Done | 8 | 8 | 0 | 7 | -1 | Day1: 8
1.2 | PB01 | Integration frontend + backend | Thang | Done | 8 | 8 | 0 | 8 | 0 | Day2: 8
1.3 | PB01 | Write frontend code | Khoa | Done | 8 | 8 | 0 | 8 | 0 | Day4: 8
1.4 | PB01 | Write API create | Khoa | Done | 6 | 6 | 0 | 7 | 1 | Day4: 6
1.5 | PB01 | Write test case | None | Not Started | 5 |  | 5 |  | -5
1.6 | PB01 | Test & Fix | None | Not Started | 5 |  | 5 |  | -5
1.7 | PB02 | Design UI | Cuong | Done | 4 | 4 | 0 | 4 | 0 | Day1: 4
1.8 | PB02 | Integration frontend + backend | Thang | Done | 7 | 7 | 0 | 7 | 0 | Day3: 7
1.9 | PB02 | Write frontend code | Cuong | Done | 8 | 8 | 0 | 7 | -1 | Day4: 8
1.1 | PB02 | Write API login | Cuong | Done | 8 | 8 | 0 | 7 | -1 | Day5: 8
1.11 | PB02 | Write test case | None | Not Started | 4 |  | 4 |  | -4
1.12 | PB02 | Test & Fix | None | Not Started | 4 |  | 4 |  | -4
1.13 | PB03 | Design UI | Khoa | Done | 3 | 3 | 0 | 3 | 0 | Day2: 3
1.14 | PB03 | Integration frontend + backend | Thang | Done | 6 | 6 | 0 | 4 | -2 | Day5: 6
1.15 | PB03 | Write frontend code | Cuong | Done | 6 | 6 | 0 | 6 | 0 | Day3: 6
1.16 | PB03 | Write API logout | Cuong | Done | 6 | 6 | 0 | 8 | 2 | Day3: 6
1.17 | PB03 | Write test case | None | Not Started | 4 |  | 4 |  | -4
1.18 | PB03 | Test & Fix | None | Not Started | 5 |  | 5 |  | -5
1.19 | PB17 | Design UI | Thang | Done | 3 | 3 | 0 | 4 | 1 | Day2: 3
1.2 | PB17 | Integration frontend + backend | Dung | Done | 5 | 5 | 0 | 4 | -1 | Day3: 5
1.21 | PB17 | Write frontend code | Dung | Done | 8 | 8 | 0 | 8 | 0 | Day5: 8
1.22 | PB17 | Write API login | Dung | Done | 8 | 8 | 0 | 7 | -1 | Day5: 8
1.23 | PB17 | Write test case | None | Not Started | 3 |  | 3 |  | -3
1.24 | PB17 | Test & Fix | None | Not Started | 3 |  | 3 |  | -3
1.25 | PB25 | Init Project | Thang | Done | 6 | 6 | 0 | 5 | -1 | Day6: 6
1.26 | PB25 | Install Libs | Dung | Done | 6 | 6 | 0 | 4 | -2 | Day6: 6
1.27 | PB25 | Config Env | Dung | Done | 10 | 10 | 0 | 8 | -2 | Day8: 10
1.28 | PB25 | Setup Server | Thang | Done | 12 | 12 | 0 | 7 | -5 | Day 10: 12
1.29 | PB25 | Write test case | None | Not Started | 6 |  | 6 |  | -6
1.3 | PB25 | Test & Fix | None | Not Started | 5 |  | 5 |  | -5
1.31 | PB26 | Design ERD | Dung | Done | 6 | 6 | 0 | 5 | -1 | Day9: 6
1.32 | PB26 | Install DB | Thang | Done | 6 | 6 | 0 | 6 | 0 | Day9: 6
1.33 | PB26 | Create Schema | Dung | Done | 12 | 12 | 0 | 12 | 0 | Day 10: 12
1.34 | PB26 | Seed Data | None | Done | 8 | 8 | 0 | 7 | -1 | Day 10: 8
1.35 | PB26 | Write test case | None | Not Started | 4 |  | 4 |  | -4
1.36 | PB26 | Test & Fix | None | Not Started | 4 |  | 4 |  | -4
|  |  |  | Total | 220 | 168 | 52 | 153 | -67 | 12 | 14 | 24 | 22 | 30 | 12 | 0 | 10 | 12 | 32
|  |  |  | Burn down | [5 empty] | 208 | 194 | 170 | 148 | 118 | 106 | 106 | 96 | 84 | 52
|  |  |  | Burn up | [5 empty] | 12 | 26 | 50 | 72 | 102 | 114 | 114 | 124 | 136 | 168
Note on A7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on B7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Backlog
Sprint Backlog 2
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
2.1 | PB04 | Design UI | Khoa | Done | 5 | 5 | 0 | 4 | -1 | Day 2: 5
2.2 | PB04 | Integration FE+BE | Thang | Done | 5 | 5 | 0 | 7 | 2 | Day 8: 5
2.3 | PB04 | Write FE code | Khoa | Done | 7 | 7 | 0 | 7 | 0 | Day 4: 7
2.4 | PB04 | Write API | Khoa | Done | 7 | 7 | 0 | 8 | 1 | Day 5: 7
2.5 | PB04 | Write test case | None | Not Started | 4 |  | 4 |  | -4
2.6 | PB04 | Test & Fix | None | Not Started | 6 |  | 6 |  | -6
2.7 | PB05 | Design UI | Khoa | Done | 5 | 5 | 0 | 5 | 0 | Day 1: 5
2.8 | PB05 | Integration FE+BE | Thang | Done | 8 | 8 | 0 | 7 | -1 | Day 7: 8
2.9 | PB05 | Write FE code | Cuong | Done | 6 | 6 | 0 | 6 | 0 | Day 3: 6
2.1 | PB05 | Write API | Cuong | Done | 8 | 8 | 0 | 7 | -1 | Day 5: 8
2.11 | PB05 | Write test case | None | Not Started | 4 |  | 4 |  | -4
2.12 | PB05 | Test & Fix | None | Not Started | 7 |  | 7 |  | -7
2.13 | PB06 | Design UI | Cuong | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
2.14 | PB06 | Integration FE+BE | Thang | Done | 7 | 7 | 0 | 7 | 0 | Day 7: 7
2.15 | PB06 | Write FE code | Cuong | Done | 6 | 6 | 0 | 7 | 1 | Day 3: 6
2.16 | PB06 | Write API | Cuong | Done | 8 | 8 | 0 | 9 | 1 | Day 5: 8
2.17 | PB06 | Write test case | None | Not Started | 4 |  | 4 |  | -4
2.18 | PB06 | Test & Fix | None | Not Started | 7 |  | 7 |  | -7
2.19 | PB07 | Design UI | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 2: 4
2.2 | PB07 | Integration FE+BE | Thang | Done | 7 | 7 | 0 | 7 | 0 | Day 8: 7
2.21 | PB07 | Write FE code | Khoa | Done | 6 | 6 | 0 | 6 | 0 | Day 4: 6
2.22 | PB07 | Write API | Khoa | Done | 8 | 8 | 0 | 8 | 0 | Day 6: 8
2.23 | PB07 | Write test case | None | Not Started | 3 |  | 3 |  | -3
2.24 | PB07 | Test & Fix | None | Not Started | 6 |  | 6 |  | -6
2.25 | PB15 | Design UI | Khoa | Done | 6 | 6 | 0 | 5 | -1 | Day 1: 6
2.26 | PB15 | Integration FE+BE | Thang | Done | 6 | 6 | 0 | 7 | 1 | Day 8: 6
2.27 | PB15 | Write FE code | Khoa | Done | 8 | 8 | 0 | 7 | -1 | Day 4: 8
2.28 | PB15 | Write API | Khoa | Done | 8 | 8 | 0 | 7 | -1 | Day 6: 8
2.29 | PB15 | Write test case | None | Not Started | 4 |  | 4 |  | -4
2.3 | PB15 | Test & Fix | None | Not Started | 5 |  | 5 |  | -5
2.31 | PB18 | Design UI | Thang | Done | 5 | 5 | 0 | 3 | -2 | Day 1: 5
2.32 | PB18 | Integration FE+BE | Dung | Done | 8 | 8 | 0 | 8 | 0 | Day 9: 8
2.33 | PB18 | Write FE code | Thang | Done | 6 | 6 | 0 | 7 | 1 | Day 4: 6
2.34 | PB18 | Write API | Dung | Done | 8 | 8 | 0 | 7 | -1 | Day 6: 8
2.35 | PB18 | Write test case | Dung | Done | 4 | 4 | 0 | 5 | 1 | Day 11: 4
2.36 | PB18 | Test & Fix | Dung | Done | 6 | 6 | 0 | 7 | 1 | Day 12: 6
2.37 | PB19 | Design UI | Thang | Done | 6 | 6 | 0 | 7 | 1 | Day 2: 6
2.38 | PB19 | Integration FE+BE | Thang | Done | 9 | 9 | 0 | 9 | 0 | Day 9: 9
2.39 | PB19 | Write FE code | Dung | Done | 5 | 5 | 0 | 4 | -1 | Day 4: 6
2.4 | PB19 | Write API | Dung | Done | 7 | 7 | 0 | 8 | 1 | Day 6: 7
2.41 | PB19 | Write test case | Dung | Done | 4 | 4 | 0 | 5 | 1 | Day 11: 4
2.42 | PB19 | Test & Fix | Thang | Done | 4 | 4 | 0 | 4 | 0 | Day 12: 4
2.43 | PB20 | Design UI | Thang | Done | 6 | 6 | 0 | 5 | -1 | Day 2: 6
2.44 | PB20 | Integration FE+BE | Thang | Done | 6 | 6 | 0 | 7 | 1 | Day 10: 6
2.45 | PB20 | Write FE code | Thang | Done | 6 | 6 | 0 | 6 | 0 | Day 5: 6
2.46 | PB20 | Write API | Dung | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 8
2.47 | PB20 | Write test case | Dung | Done | 6 | 6 | 0 | 5 | -1 | Day 11: 6
2.48 | PB20 | Test & Fix | Thang | Done | 6 | 6 | 0 | 7 | 1 | Day 13: 6
2.49 | PB22 | Design UI | Dung | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
2.5 | PB22 | Integration FE+BE | Dung | Done | 6 | 6 | 0 | 7 | 1 | Day 9: 6
2.51 | PB22 | Write FE code | Dung | Done | 5 | 5 | 0 | 6 | 1 | Day 5: 5
2.52 | PB22 | Write API | Dung | Done | 8 | 8 | 0 | 8 | 0 | Day 6: 8
2.53 | PB22 | Write test case | Thang | Done | 4 | 4 | 0 | 5 | 1 | Day 11: 4
2.54 | PB22 | Test & Fix | Thang | Done | 6 | 6 | 0 | 5 | -1 | Day 13: 6
2.55 | PB27 | Design Logic Flow | Khoa | Done | 10 | 10 | 0 | 9 | -1 | Day 16: 10
2.56 | PB27 | Integration | Thang | Done | 10 | 10 | 0 | 7 | -3 | Day 19: 10
2.57 | PB27 | Write Core Logic | Thang | Done | 15 | 15 | 0 | 17 | 2 | Day 17: 15
2.58 | PB27 | Write API | Cuong | Done | 10 | 10 | 0 | 10 | 0 | Day 16: 10
2.59 | PB27 | Write test case | Khoa | Done | 7 | 7 | 0 | 7 | 0 | Day 21: 7
2.6 | PB27 | Test & Fix | Cuong | Done | 8 | 8 | 0 | 8 | 0 | Day 22: 8
1.5 | PB01 | Write test case | Cuong | Done | 5 | 5 | 0 | 5 | 0 | Day 25: 5
1.6 | PB01 | Test & Fix | Cuong | Done | 5 | 5 | 0 | 6 | 1 | Day 26: 5
1.11 | PB02 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 25: 4
1.12 | PB02 | Test & Fix | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
1.17 | PB03 | Write test case | Cuong | Done | 4 | 4 | 0 | 4 | 0 | Day 25: 4
1.18 | PB03 | Test & Fix | Cuong | Done | 5 | 5 | 0 | 6 | 1 | Day 28: 5
1.23 | PB17 | Write test case | Khoa | Done | 3 | 3 | 0 | 3 | 0 | Day 25: 3
1.24 | PB17 | Test & Fix | Khoa | Done | 3 | 3 | 0 | 5 | 2 | Day 28: 3
1.29 | PB25 | Write test case | Cuong | Done | 6 | 6 | 0 | 4 | -2 | Day 25: 6
1.3 | PB25 | Test & Fix | Cuong | Done | 5 | 5 | 0 | 7 | 2 | Day 30: 5
1.35 | PB26 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 25: 4
1.36 | PB26 | Test & Fix | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 30: 4
|  |  |  | Total | 434 | 239 | 9 | 241 | -48 | 24 | 21 | 12 | 33 | 42 | 39 | 15 | 18 | 23 | 6 | 18 | 10 | 12 | 0 | 0 | 20 | 15 | 0 | 10 | 0 | 7 | 8 | 0 | 0 | 26 | 9 | 0 | 8 | 0 | 9
|  |  |  | Burn down | [5 empty] | 410 | 389 | 377 | 344 | 302 | 263 | 248 | 230 | 207 | 201 | 183 | 173 | 161 | 161 | 161 | 141 | 126 | 126 | 116 | 116 | 109 | 101 | 101 | 101 | 75 | 66 | 66 | 58 | 58 | 49
|  |  |  | Burn up | [5 empty] | 24 | 45 | 57 | 90 | 132 | 171 | 186 | 204 | 227 | 233 | 251 | 261 | 273 | 273 | 273 | 293 | 308 | 308 | 318 | 318 | 325 | 333 | 333 | 333 | 359 | 368 | 368 | 376 | 376 | 385
Note on A7: ====== ID#AAABW84Drls jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on B7: ====== ID#AAABW84Drlo jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Backlog
Sprint Backlog 3
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32
3.1 | PB08 | Design UI | Cuong | Done | 4 | 4 | 0 | 4 | 0 | Day 2: 4
3.2 | PB08 | Integration FE+BE | Thang | Done | 10 | 10 | 0 | 9 | -1 | Day 16: 10
3.3 | PB08 | Write FE code | Cuong | Done | 8 | 8 | 0 | 8 | 0 | Day 6: 8
3.4 | PB08 | Write API | Cuong | Done | 14 | 14 | 0 | 14 | 0 | Day 11: 14
3.5 | PB08 | Write test case | None | Not Started | 4 |  | 4 |  | -4
3.6 | PB08 | Test & Fix | None | Not Started | 6 |  | 6 |  | -6
3.7 | PB10 | Design UI | Dung | Done | 4 | 4 | 0 | 4 | 0 | Day 3: 4
3.8 | PB10 | Integration FE+BE | Thang | Done | 10 | 10 | 0 | 10 | 0 | Day 18: 10
3.9 | PB10 | Write FE code | Cuong | Done | 8 | 8 | 0 | 10 | 2 | Day 8: 8
3.1 | PB10 | Write API | Dung | Done | 14 | 14 | 0 | 12 | -2 | Day 13: 14
3.11 | PB10 | Write test case | None | Not Started | 4 |  | 4 |  | -4
3.12 | PB10 | Test & Fix | None | Not Started | 6 |  | 6 |  | -6
3.13 | PB13 | Design UI | Khoa | Done | 4 | 4 | 0 | 3 | -1 | Day 4: 4
3.14 | PB13 | Integration FE+BE | Thang | Done | 10 | 10 | 0 | 10 | 0 | Day 19: 10
3.15 | PB13 | Write FE code | Khoa | Done | 8 | 8 | 0 | 7 | -1 | Day 9: 8
3.16 | PB13 | Write API | Khoa | Done | 14 | 14 | 0 | 15 | 1 | Day 14: 14
3.17 | PB13 | Write test case | None | Not Started | 4 |  | 4 |  | -4
3.18 | PB13 | Test & Fix | None | Not Started | 6 |  | 6 |  | -6
3.19 | PB14 | Design UI | Khoa | Done | 4 | 4 | 0 | 2 | -2 | Day 5: 4
3.2 | PB14 | Integration FE+BE | Thang | Done | 10 | 10 | 0 | 10 | 0 | Day 20: 10
3.21 | PB14 | Write FE code | Khoa | Done | 8 | 8 | 0 | 9 | 1 | Day 10: 8
3.22 | PB14 | Write API | Thang | Done | 14 | 14 | 0 | 14 | 0 | Day 15: 14
3.23 | PB14 | Write test case | None | Not Started | 4 |  | 4 |  | -4
3.24 | PB14 | Test & Fix | None | Not Started | 6 |  | 6 |  | -6
3.25 | PB16 | Design UI | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 6: 4
3.26 | PB16 | Integration FE+BE | Cuong | Done | 10 | 10 | 0 | 9 | -1 | Day 21: 10
3.27 | PB16 | Write FE code | Cuong | Done | 8 | 8 | 0 | 8 | 0 | Day 11: 8
3.28 | PB16 | Write API | Thang | Done | 14 | 14 | 0 | 12 | -2 | Day 16: 14
3.29 | PB16 | Write test case | Khoa | Done | 4 | 4 | 0 | 5 | 1 | Day 29: 4
3.3 | PB16 | Test & Fix | Cuong | Done | 6 | 6 | 0 | 8 | 2 | Day 31: 6
3.31 | PB21 | Design UI | Dung | Done | 4 | 4 | 0 | 4 | 0 | Day 3: 4
3.32 | PB21 | Integration FE+BE | Dung | Done | 10 | 10 | 0 | 8 | -2 | Day 17: 10
3.33 | PB21 | Write FE code | Thang | Done | 8 | 8 | 0 | 8 | 0 | Day 8: 8
3.34 | PB21 | Write API | Dung | Done | 14 | 14 | 0 | 12 | -2 | Day 12: 14
3.35 | PB21 | Write test case | Thang | Done | 4 | 4 | 0 | 4 | 0 | Day 24: 4
3.36 | PB21 | Test & Fix | Dung | Done | 6 | 6 | 0 | 6 | 0 | Day 25: 6
3.37 | PB23 | Design UI | Thang | Done | 4 | 4 | 0 | 4 | 0 | Day 4: 4
3.38 | PB23 | Integration FE+BE | Dung | Done | 10 | 10 | 0 | 11 | 1 | Day 18: 10
3.39 | PB23 | Write FE code | Thang | Done | 8 | 8 | 0 | 8 | 0 | Day 9: 8
3.4 | PB23 | Write API | Dung | Done | 14 | 14 | 0 | 12 | -2 | Day 13: 14
3.41 | PB23 | Write test case | Dung | Done | 4 | 4 | 0 | 4 | 0 | Day 24: 4
3.42 | PB23 | Test & Fix | Dung | Done | 6 | 6 | 0 | 6 | 0 | Day 25: 6
3.43 | PB29 | Analyze video processing requirements | Cuong | Done | 10 | 10 | 0 | 8 | -2 | Day 7: 10
3.44 | PB29 | Design video processing pipeline | Khoa | Done | 12 | 12 | 0 | 14 | 2 | Day 10: 12
3.45 | PB29 | Implement core video handler module | Thang | Done | 24 | 24 | 0 | 25 | 1 | Day 20: 24
3.46 | PB29 | Implement backend API for video I/O | Thang | Done | 20 | 20 | 0 | 24 | 4 | Day 22: 12
3.47 | PB29 | Write unit tests for core logic | Thang | Not Started | 12 | 0 | 12 | 0 | 0
3.48 | PB29 | Performance test + Fixing | Dung | Not Started | 16 | 0 | 16 | 0 | 0 | Day 26: 16
3.49 | PB30 | Analyze camera protocols & requirements | Cuong | Done | 10 | 10 | 0 | 10 | 0 | Day 8: 10
3.5 | PB30 | Design camera connection architecture | Khoa | Done | 12 | 12 | 0 | 14 | 2 | Day 12: 12
3.51 | PB30 | Implement camera connection module | Thang | Done | 20 | 20 | 0 | 22 | 2 | Day 21: 20
3.52 | PB30 | Implement streaming transport API | Thang | Done | 20 | 20 | 0 | 19 | -1 | Day 22: 20
3.53 | PB30 | Unit testing (network + streaming) | Dung | Not Started | 14 | 14 | 0 | 15 | 1 | Day 29: 14
3.54 | PB30 | Stability test & Fix | Thang | Not Started | 16 | 16 | 0 | 16 | 0 | Day 31: 16
3.55 | PB04 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 23: 4
3.56 | PB04 | Test & Fix | Khoa | Done | 7 | 7 | 0 | 7 | 0 | Day 25: 7
3.57 | PB05 | Write test case | Cuong | Done | 4 | 4 | 0 | 4 | 0 | Day 24: 4
3.58 | PB05 | Test & Fix | Cuong | Done | 7 | 7 | 0 | 7 | 0 | Day 26: 7
3.59 | PB06 | Write test case | Cuong | Done | 3 | 3 | 0 | 3 | 0 | Day 25: 3
3.6 | PB06 | Test & Fix | Thang | Done | 3 | 3 | 0 | 3 | 0 | Day 27: 3
3.61 | PB07 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
3.62 | PB07 | Test & Fix | Thang | Done | 4 | 4 | 0 | 4 | 0 | Day 28: 4
3.63 | PB15 | Write test case | Dung | Done | 6 | 6 | 0 | 6 | 0 | Day 30: 6
3.64 | PB15 | Test & Fix | Dung | Done | 6 | 6 | 0 | 6 | 0 | Day 29: 6
|  |  |  | Total | 508 | 440 | 68 | 441 | -39 | 0 | 0 | 4 | 8 | 4 | 4 | 10 | 18 | 16 | 20 | 8 | 26 | 14 | 14 | 14 | 14 | 10 | 10 | 10 | 34 | 30 | 12 | 20 | 4 | 12 | 22 | 27 | 3 | 4 | 24 | 6 | 22 | 0
|  |  |  | Burn down | [5 empty] | 508 | 508 | 504 | 496 | 492 | 488 | 478 | 460 | 444 | 424 | 416 | 390 | 376 | 362 | 348 | 334 | 324 | 314 | 304 | 270 | 240 | 228 | 208 | 204 | 192 | 170 | 143 | 140 | 136 | 112 | 106 | 84 | 84
|  |  |  | Burn up | [5 empty] | 0 | 0 | 4 | 12 | 16 | 20 | 30 | 48 | 64 | 84 | 92 | 118 | 132 | 146 | 160 | 174 | 184 | 194 | 204 | 238 | 268 | 280 | 300 | 304 | 316 | 338 | 365 | 368 | 372 | 396 | 402 | 424 | 424

## Sprint 4 Backlog
Sprint Backlog 4
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26
1 | PB09 | Design UI | Khoa | Done | 3 | 3 | 0 | 3 | 0 | Day 4: 3
1.1 | PB09 | Write FE code | Cuong | Done | 5 | 5 | 0 | 5 | 0 | Day 11: 5
1.2 | PB09 | Write API | Cuong | Done | 7 | 7 | 0 | 7 | 0 | Day 12: 7
1.3 | PB09 | Integration FE+BE | Thang | Done | 4 | 4 | 0 | 4 | 0 | Day 20: 4
1.4 | PB09 | Write test case | None | Not Started | 2 |  | 2 |  | -2
1.5 | PB09 | Test & Fix | None | Not Started | 4 |  | 4 |  | 0 | Day 14: 4
1.6 | PB11 | Design UI | Khoa | Done | 3 | 3 | 0 | 3 | 0 | Day 5: 3
1.7 | PB11 | Write FE code | Cuong | Done | 6 | 6 | 0 | 6 | 0 | Day 8: 6
1.8 | PB11 | Write API | Cuong | Done | 8 | 8 | 0 | 8 | 0 | Day 12: 8
1.9 | PB11 | Integration FE+BE | Thang | Done | 5 | 5 | 0 | 5 | 0 | Day 12: 5
2 | PB11 | Write test case | None | Not Started | 3 |  | 3 |  | -3
2.1 | PB11 | Test & Fix | None | Not Started | 5 |  | 5 |  | -5
2.2 | PB12 | Design UI | Khoa | Done | 3 | 3 | 0 | 3 | 0 | Day 2: 3
2.3 | PB12 | Write FE code | Cuong | Done | 6 | 6 | 0 | 6 | 0 | Day 10: 6
2.4 | PB12 | Write API | Khoa | Done | 8 | 8 | 0 | 8 | 0 | Day 10: 8
2.5 | PB12 | Integration FE+BE | Thang | Done | 5 | 5 | 0 | 5 | 0 | Day 13: 5
2.6 | PB12 | Write test case | None | Not Started | 3 |  | 3 |  | -3
2.7 | PB12 | Test & Fix | None | Not Started | 5 |  | 5 |  | 0 | Day 18: 5
2.8 | PB24 | Design UI | Khoa | Done | 2 | 2 | 0 | 2 | 0 | Day 2: 2
2.9 | PB24 | Write FE code | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 10: 4
3 | PB24 | Write API | Cuong | Done | 6 | 6 | 0 | 6 | 0 | Day 15: 6
3.1 | PB24 | Integration FE+BE | Thang | Done | 3 | 3 | 0 | 3 | 0 | Day 17: 3
3.2 | PB24 | Write test case | None | Not Started | 2 |  | 2 |  | -2
3.3 | PB24 | Test & Fix | None | Not Started | 3 |  | 3 |  | -3
3.4 | PB04 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 23: 4
3.5 | PB04 | Test & Fix | Cuong | Ongoing | 7 | 5 | 2 | 5 | -2 | Day 23: 5
3.6 | PB05 | Write test case | Thang | Done | 4 | 4 | 0 | 4 | 0 | Day 20: 4
3.7 | PB05 | Test & Fix | Dung | Done | 7 | 7 | 0 | 7 | 0 | Day 23: 7
3.8 | PB06 | Write test case | Cuong | Done | 3 | 3 | 0 | 3 | 0 | Day 21: 3
3.9 | PB06 | Test & Fix | Cuong | Done | 3 | 3 | 0 | 3 | 0 | Day 23: 3
4 | PB07 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 21: 4
4.1 | PB07 | Test & Fix | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 24: 4
4.2 | PB15 | Write test case | Dung | Done | 6 | 6 | 0 | 6 | 0 | Day 20: 6
4.3 | PB15 | Test & Fix | Dung | Ongoing | 6 | 4 | 2 | 3 | -3 | Day 24: 4
4.4 | PB08 | Write test case | Dung | Done | 4 | 4 | 0 | 4 | 0 | Day 20: 4
4.5 | PB08 | Test & Fix | Dung | Done | 7 | 7 | 0 | 7 | 0 | Day 23: 7
4.6 | PB10 | Write test case | Cuong | Done | 4 | 4 | 0 | 4 | 0 | Day 21: 4
4.7 | PB10 | Test & Fix | Dung | Done | 7 | 7 | 0 | 7 | 0 | Day 24: 7
4.8 | PB13 | Write test case | Khoa | Done | 4 | 4 | 0 | 4 | 0 | Day 23: 4
4.9 | PB13 | Test & Fix | Thang | Done | 6 | 6 | 0 | 6 | 0 | Day 24: 6
5 | PB14 | Write test case | None | Not Started | 4 |  | 4 |  | 0 | Day 26: 4
5.1 | PB14 | Test & Fix | None | Not Started | 6 |  | 6 |  | 0 | Day 25: 6
|  |  |  | Total | 195 | 148 | 31 | 147 | -23 | 0 | 5 | 0 | 3 | 3 | 0 | 0 | 6 | 0 | 18 | 5 | 20 | 5 | 4 | 6 | 0 | 3 | 5 | 0 | 18 | 11 | 0 | 30 | 21 | 6 | 4
|  |  |  | Burn down | [5 empty] | 195 | 190 | 190 | 187 | 184 | 184 | 184 | 178 | 178 | 160 | 155 | 135 | 130 | 126 | 120 | 120 | 117 | 112 | 112 | 94 | 83 | 83 | 53 | 32 | 26 | 22
|  |  |  | Burn up | [5 empty] | 0 | 5 | 5 | 8 | 11 | 11 | 11 | 17 | 17 | 35 | 40 | 60 | 65 | 69 | 75 | 75 | 78 | 83 | 83 | 101 | 112 | 112 | 142 | 163 | 169 | 173